## Project schedule pt. 1
| Primevision | [5 empty] | Project start: | [7 empty] | 2024-09-02
| G1 | [5 empty] | Display week: | [7 empty] | 1
Part 1 of 2
[7 empty] | 2024-09-02 | [6 empty] | 2024-09-09 | [6 empty] | 2024-09-16 | [6 empty] | 2024-09-23 | [6 empty] | 2024-09-30 | [6 empty] | 2024-10-07 | [6 empty] | 2024-10-14 | [6 empty] | 2024-10-21
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2024-09-02 to 2024-10-27
 | time axis 2024-09-02 to 2024-10-27
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Sprint Week 1
| Github structuring | Tom | 100% | 2024-09-10 | 2024-09-12 | 3
| Gant chart planning | Jelmer | 100% | 2024-09-10 | 2024-09-12 | 3
| Main- and subquestions formulation | All | 100% | 2024-09-10 | 2024-09-12 | 3
| Data preperation | Mats | 100% | 2024-09-10 | 2024-09-12 | 3
| Hand-in Deliverable | Sun + Jelmer | 0% | 2024-09-12 | 2024-09-12
Sprint Week 2
| Subq1. Correlation Chart | Kristian | 100% | 2024-09-16 | 2024-09-22 | 7
| Subq1. Frequency and total chart | Mats | 100% | 2024-09-16 | 2024-09-22 | 7
| Subq1. Location analysis | Tom | 100% | 2024-09-16 | 2024-09-22 | 7
| Subq1. Outlier/distribution analysis | Jelmer | 100% | 2024-09-16 | 2024-09-22 | 7
| Subq1. Feature extraction | Sun | 100% | 2024-09-16 | 2024-09-22
Model forming
| Model forming brainstorm | All | 100% | 2024-09-24 | 2024-09-24
| Documentation mainbook | All | 100% | 2024-09-24 | 2024-09-29
| Developing NN | Mats | 100% | 2024-09-24 | 2024-09-29
| Seasonality inclusion | Kristian | 100% | 2024-09-24 | 2024-09-29
| Developing ARIMA | Tom | 100% | 2024-09-24 | 2024-09-29
| Developing LSTM | Sun | 100% | 2024-09-24 | 2024-09-29
| Explroing CEEMDAN possibilities | Jelmer | 100% | 2024-09-24 | 2024-09-29
Midterm check
| Discuss results | All | 100% | 2024-10-01 | 2024-10-01 | 1
| Developing dashboard | Tom | 100% | 2024-10-01 | 2024-10-06 | 6
| Improve chosen models | All | 100% | 2024-10-01 | 2024-10-06 | 6
| Creating presentation | Jelmer | 100% | 2024-10-07 | 2024-10-07
| Midterm check presentation | All | 100% | 2024-10-08 | 2024-10-08
Insert new rows ABOVE this one

## Project schedule pt. 2
| Primevision | [5 empty] | Project start: | [7 empty] | 2024-10-10
| G1 | [5 empty] | Display week: | [7 empty] | 1
Part 2 of 2
[7 empty] | 2024-10-07 | [6 empty] | 2024-10-14 | [6 empty] | 2024-10-21 | [6 empty] | 2024-10-28 | [6 empty] | 2024-11-04 | [6 empty] | 2024-11-11 | [6 empty] | 2024-11-18 | [6 empty] | 2024-11-25
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2024-10-07 to 2024-12-01
 | time axis 2024-10-07 to 2024-12-01
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Comparing models
| Improve ARIMA + add benchmarks | Tom | 100% | 2024-10-08 | 2024-10-15 | 8
| Improve NN + add benchmarks | Mats | 100% | 2024-10-08 | 2024-10-15 | 8
| Improve Linear + add benchmarks | Kristian | 100% | 2024-10-08 | 2024-10-15 | 8
| Improve LSTM + add benchmarks | Sun + Jelmer | 100% | 2024-10-08 | 2024-10-15 | 8
| Improve CEEMDAN LSTM/GRU | Sun + Jelmer | 100% | 2024-10-08 | 2024-10-15 | 8
Model choice
| Finish ARIMA + add benchmarks | Tom | 100% | 2024-10-15 | 2024-10-22
| Finish NN + add benchmarks | Mats | 100% | 2024-10-15 | 2024-10-22
| Finish Linear + add benchmarks | Kristian | 100% | 2024-10-15 | 2024-10-22
| Finish LSTM + add benchmarks | Jelmer | 100% | 2024-10-15 | 2024-10-22
| Explore parralel computing for CEEMDAN | Sun | 100% | 2024-10-15 | 2024-10-22
Result analysis
| Result discussion | All | 100% | 2024-10-21 | 2024-10-21 | 1
| Result reporting models NN + ARIMA + Lin | Tom + Mats + Kristian | 100% | 2024-10-21 | 2024-10-29 | 9
| Result reporting model LSTM/GRU | Sun + Jelmer | 100% | 2024-10-21 | 2024-10-29
| Result reporting model LSTM/GRU | Sun + Jelmer | 100% | 2024-10-21 | 2024-10-29 | 9
| Result table | All | 100% | 2024-10-24 | 2024-10-29
| Conclusion + Introduction | Jelmer | 100% | 2024-10-24 | 2024-10-29
| Notebook + Github Documentation | Kristian | 100% | 2024-10-21 | 2024-10-29
| Finish dashboarding | Tom | 100% | 2024-10-21 | 2024-10-29 | 9
| Hand-in Final delivery | All | 0% | 2024-10-29 | 2024-10-30 | 2
Presentation and final sprint
| Portfolio submission | all | 0% | 2024-10-30 | 2024-10-30 | 1
| Powerpoint | Kristian | 0% | 2024-10-30 | 2024-11-03 | 5
| Powerpoint text ARIMA + NN + Lin | Tom + Mats + Kristian | 0% | 2024-10-30 | 2024-11-03 | 5
| Powerpoint text model LSTM/CEEMDAN | Sun + Jelmer | 0% | 2024-10-30 | 2024-11-03 | 5
| Final Presentation | all | 0% | 2024-11-04 | 2024-11-04
Insert new rows ABOVE this one